TEMPLATE

Website project plan

Six phases, the feedback rounds inside each, the sign-off that closes each one, and the dates. Fill in the dates backwards from launch, agree the rounds before the first link goes out, and name one approver.

The shape of the project

| Phase | Produces | Rounds included | Closed by |
| --- | --- | --- | --- |
| 1. Discovery | Brief, sitemap, content inventory | 1 | Brief approved |
| 2. Design | Wireframes, then visual design | 2 wireframe, 3 design | Design approved |
| 3. Content | Copy and assets per page | 2 | Content approved |
| 4. Build | Staging site | 2 | Staging approved |
| 5. Launch | Live site, redirects, tracking | 1 | Launch approved |
| 6. Aftercare | Fixes and the first review | 1 | Project closed |

Three rounds on design and two on the build is the shape most agencies settle on. If your contract says something different, change the numbers; the point is that they are written down before anyone sends a link.

Project

| Client |  |
| --- | --- |
| Project |  |
| Agency lead |  |
| Client lead (the one person who approves) |  |
| Start date |  |
| Target launch |  |
| Where feedback happens | one review link per phase, comments pinned to the thing; email is for scheduling only |

Phase 1: Discovery

| Produces | the brief, the sitemap, a content inventory of what exists and what is new. |
| --- | --- |
| Reviewed by | client lead. |
| Rounds included | one. |
| Closed by | brief approved, with a name and a date. |
| Due |  |

Phase 2: Design

| Produces | wireframes for the key pages, then visual design for the same pages, then the remaining pages from the approved system. |
| --- | --- |
| Reviewed by | client lead, plus anyone the client lead names; feedback from others goes through the client lead. |
| Rounds included | two on wireframes, three on visual design. A round is one review link sent and one set of feedback received. |
| Closed by | design approved. After approval, design changes are a change request, estimated separately. |
| Due | wireframes ______________, design ______________ |

Phase 3: Content

| Produces | final copy and assets for every page in the sitemap. |
| --- | --- |
| Reviewed by | client lead. |
| Rounds included | two. |
| Closed by | content approved. Content that arrives after this date moves the launch date by the same number of days. |
| Due |  |

Phase 4: Build

| Produces | the site on a staging link, every page, every form working. |
| --- | --- |
| Reviewed by | the agency first (the technical pass: links, forms, widths, browsers, speed), then the client lead (the content pass: words, images, order, calls to action). |
| Rounds included | two client rounds on staging. |
| Closed by | staging approved. |
| Due |  |

Phase 5: Launch

| Produces | the live site, redirects from old URLs, analytics and search console verified, forms tested live. |
| --- | --- |
| Reviewed by | client lead, same day. |
| Rounds included | one, for launch-day fixes only. |
| Closed by | launch approved. |
| Launch date |  |

Phase 6: Aftercare

| Produces | fixes raised in the first two weeks, and a 30-day review of analytics and search. |
| --- | --- |
| Rounds included | one. |
| Closed by | project closed; ongoing work moves to a retainer or a new quote. |
| Due |  |

Rules we both agree to

| 1. | One person on each side approves. Other people can comment; the two leads decide. |
| --- | --- |
| 2. | Feedback goes on the review link, pinned to the thing it is about. Email is for scheduling. |
| 3. | A round is a round. Feedback that arrives after a round closes goes into the next round or a change request. |
| 4. | Approval is recorded with a name and a date, and it is final for that phase. |
| 5. | A missed feedback deadline moves the launch date by the same number of days. |